PARTNER SEARCH FORM

| Programme (delete as appropriate) | Tempus: Joint Project Programme theme: Knowledge triangle: education-innovation-research Multi-country project |
| --- | --- |
| Preliminary project title | Knowledge database “Insti-Tube” |

Who we are

| Name of institution |  | Russian-Tajik Slavonic University |
| --- | --- | --- |
| Type of institution |  | Interstate higher education |
| City |  | Dushanbe |
| Address |  | 30 Tursun-zade Str. |
| Telephone |  | +992 918 613 427 |
| E-mail |  | umed.ulugov@youth21.tj |
| Website |  | http://www.rtsu-slavist.tj/ |
| Contact person | Name | Umidjon Ulugov |
|  | Position | Head of the department on coordination of programs, projects and grants in the fields of education and science |
|  | Telephone | +992918613427 |
|  | E-mail | umed.ulugov@youth21.tj |

Our project idea

| Objectives | 1. Analyze the current system of interactive training methods in 5 countries of Central Asia and in EU countries; 2. Create a central server to collect all video lectures, video presentations of teachers of 8 institutes of higher education in Central Asia and EU, place a backup server, appoint administrators in each of institutes participating in the project; 3. Test system involving students and teachers and run the system in full operation; 4. Final conference, final report. |
| --- | --- |
| Activities | Ad 1. Monitoring of internal documents and institutional strategies with focus on interactive training methods 3 seminars - discussion and conclusions of the future knowledge database system; Identification of priority directions of knowledge and science in order to create a server; Ad 2. Development of 32 video courses of lectures and presentations on priority themes in 8 institutes of higher education of CA and EU; Create a central server and internet-platform to download the existing information; Place backup servers based on each of institutes providing with the local access for students and teachers; Appoint the responsible administrators in order to coordinate in-site servers; Ad. 3 Involve up to 8000 students and teachers of 8 institutes in CA and EU to assess knowledge database; Give a final assessment of the system work and analyze the shortcomings; Introduce changes based on users’ opinions and put the system in full operation. Ad 4. Conduct a final conference with the countries participating in the project in Dushanbe; Draw up a Memorandum on partnership and cooperation to ensure the proper servers operation, sharing of information and constant database updating; Develop and circulate appeal to other universities of the world to join the project. |
| Outputs | General analytical report on existing and innovative approaches to education, and the use of video materials in process of teaching of students and specialists; Central and local servers to collect and disseminate knowledge; Final assessment of the system availability based on beneficiaries’ opinions; Development of documents on future project sustainability. |
| Working language | English |
| Duration | 36 months |

We are searching for

| Types of institutions, countries, etc. | Higher Education Institutions Region: Central Asia: Kazakhstan, Tajikistan, Kyrgystan, Turkmenistan and Uzbekistan National priority: Knowledge triangle: education-innovation-research Regional priority: Knowledge triangle: education-innovation-research |
| --- | --- |

If you are interested to develop together with our institution the project as described above

please do not hesitate to write to our contact person.