# 6th TEMPUS call

PROPOSAL FORM

Joint Project

Project title: Development of Sustainable Labour Market via Career Guidance Networking in Armenia, Moldova, Russia

Project acronym: DeCar

Priority reference:

Higher Education and Society (Development of partnerships with enterprises)

Draft summary of the project

Duration – 3 years

Budget -

Partners

EU

|  | Country | Organisation | Short name | Contact person | e-mail |
| --- | --- | --- | --- | --- | --- |
|  | UK | University of West London | WLU | Deborah Lock | Deborah.Lock@uwl.ac.uk |
|  | Sweden | Royal Institute of Technology, Stockholm (TBC) | KTH | Victor Kordas | victork@kth.se |
|  | Germany | Deutsches Studentenwerk (TBC) | DSW | Danja Oste | danja.oste@studentenwerke.de |
|  | EU | European Council for Student Affairs | ECStA | Marijke Seresia | marijke.seresia@artesis.be |

Armenia

|  | Armenia | Gavar State University | GSU | Arsen Aproyan | aproyan@list.ru |
| --- | --- | --- | --- | --- | --- |
|  | Armenia | Eurasia International University | EIU | Hovhannes Harutyunyan | hovhannes.harutyunyan@eiu.am |
|  | Armenia | Republican Union of Employers of Armenia | RUEA | Nare Matevosyan | narema21@mail.ru |

Moldova

|  | Moldova | Moldova University of European Studies | USEM | Svetlana Chesari | asstreia@yahoo.com |
| --- | --- | --- | --- | --- | --- |
|  | Moldova | University from Moldova |  |  |  |
|  | Moldova | Enterprise from Moldova |  |  |  |

Russia

|  | Russia | Nizhnevartovsk State University of Humanities | NSUH | Nadezhda Nemchinova | nemchinova.na@gmail.com |
| --- | --- | --- | --- | --- | --- |
|  | Russia | Voronezh State University | VSU | Alla Akulshina | akulshina@vsu.ru |
|  |  | Penza State University | PSU | Tatiana Razuvaeva | rastan12@mail.ru |
|  | Russia | Academy of Labour and Social Relations | ATISO | Evgeny Osetrov | evgeny.osetrov@atiso.ru |
|  | Russia | Chelyabinsk State University | CSU | Liudmila Shuravina | lshuravina@csu.ru |
|  | Russia | Don State Technical University | DSTU | Irina Maevskaya | dstu_oms@mail.ru |
|  | Russia | Atos IT Solutions and Services GmbH |  |  |  |
|  | Russia | ТНК bp (to be confirmed) |  |  |  |

Tempus programme objectives, themes and priorities addressed by this application

- To promote the reform and modernisation of higher education in the partner countries

- To enhance the quality and relevance of higher education in the partner countries

- To build up the capacity of higher education institutions in the partner countries and the EU, in particular for international cooperation and for a permanent modernisation process, and to assist them in opening themselves up to society at large

- To foster the reciprocal development of human resources

- To enhance networking among higher education institutions and research institutions across the Partner Countries and EU Member States.

Overall objective of the project is to contribute to strengthening of closer cooperation of the EU with such Eastern Neighboring countries as Armenia, Moldova and Russia within the framework of Higher Education Area in accordance with Bologna process post-2010 requirements and labour market demands through development of sustainable links between higher education institutions and enterprises of the partner countries universities, and correspondently highly competitive specialist training as well as increasing the attractiveness of  the higher education systems in these countries and in the EU.

Specific objectives of the project

- Development of innovative model for HEIs-enterprises partnerships/links and institutional arrangements for Career Guidance

- Modernization of HEI-based CGC network to increase attractiveness of higher education systems in EU and Eastern Neighboring countries through efficient application of EU practices on career management.

- Developing mechanisms of employers’ involvement into curricula design, to ensure students competitiveness on the labor market.

- Implementation of career management programs at partner-universities that enable students effectively identify career goals and preferences, develop and master strategic and tactical career management skills.

- Implementation of student start up businesses to encourage young people to get involved with business and enterprises and to find out more about being self-employed, to obtain business skills such as teamwork and communication along with other proficiencies.

- Promotion of students and CGC staff mobility.

The main activities

WP1. Development of innovative model for HEIs-enterprises partnerships/links and institutional arrangements for Career Guidance.

  - Study of best EU practices in HEI-enterprise partnerships, thesaurus building.

  - Development of a universal model of CGC network.

  - Training staff from CG centers of Moldova, Armenia, Russia.

  - Developing model of CGC-enterprise cooperation in curricula design.

WP2. Establishing CGC network model in partner-universities.

  - CGC network operation planning.

  - Building infrastructure, equipping CGC centers, validation of agreements between

network members, launch of CGC network.

  - Evaluation of CGC network operation efficiency.

WP3. Implementation of career management programmes.

  - Recommendations on curricula changes of key educational programmes.

  - Introduction of special courses on career management.

  - Establishment of recruiting agencies for promotion of students’ expertise in partner HEIs.

WP4. Implementation of Student start-up businesses

  - Organization of professional competitions for students from partner-universities as part of research and development activities.

  - Establishment of a common database for student project ideas and designs.

  - Creating mobile international project teams of students to develop, pursue and introduce progressive research & technology entrepreneurial solutions, start-up business ideas.

WP5. Monitoring and quality control

5.1. Internal quality control and monitoring.

5.2. External quality control and per review.

5.3. Monitoring Reports.

WP6. Dissemination and Sustainability

6.1. Develop a web-portal.

6.2. Organization of seminars and conferences for stakeholders.

6.3. Reciprocal dissemination of the information among employer-organizations.

6.4. Final project event.

WP7. Project management and Quality control

7.1. Kick off meeting.

7.2. Consortium meeting one.

7.3. Consortium meeting two.

7.4. Consortium meeting three.

7.5. Ongoing project and financial coordination.

The main projects results

- Developed mechanisms of employers’ involvement into curricula design, to ensure that students are much sought after on the labor market.

- Modernized of HEI-based CGC network to increase attractiveness of higher education systems in EU and Eastern Neighboring countries through efficient application of EU practices on career management.

- Developed innovative model for HEIs-enterprises partnerships/links and institutional arrangements for Career Guidance.

- Established CGC network model in partner-universities.

- Career management programmes implemented.

- Built up student start-up businesses.

- Enhanced students and CGC staff mobility.